School Management System

Local-First Multi-Tenant SaaS

Product Backlog

Prototype → MVP → Roadmap — epics, stories, acceptance criteria

| Field | Value |
| --- | --- |
| Project | SMS SaaS — Local-First Multi-tenant |
| Prepared for | Immanuel · Lish Technical Consulting |
| Document type | Product Backlog |
| Version | 0.1 (Prototype phase) |
| Date | 2026-05-12 |
| Status | Draft for stakeholder review |
| Cloud target | GCP Cloud Run + Cloud SQL · africa-south1 (Johannesburg) |
| Pricing model | Micro-access via M-Pesa STK Push + school flat fee |

# 1. Backlog Overview

This product backlog is the sprint-ready breakdown of the SRS. Every user story traces back to one or more SRS functional requirements (FR-*) so coverage is auditable. Stories are grouped into epics and tagged with priority and phase.

## 1.1 Priority and phase tags

| Tag | Meaning |
| --- | --- |
| P0 · Prototype | Must ship in the prototype demo |
| P1 · MVP | Required for first paying school |
| P2 · Roadmap | Future iteration; not estimated in detail |

## 1.2 Estimation scale

- 1 point — trivial; under a day

- 2 points — small; 1–2 days

- 3 points — medium; 3–5 days

- 5 points — substantial; about a week

- 8 points — large; needs decomposition before sprint start

- 13 points — too big; must be split

## 1.3 Definition of Ready

- Story has a single clear actor and outcome

- Acceptance criteria are testable, not aspirational

- Estimated and prioritised

- Dependencies identified

- Linked SRS requirement(s) referenced

## 1.4 Definition of Done

- Code merged to `main`

- Unit tests written and passing

- Integration tests written for any new API endpoint

- Acceptance criteria demonstrably met (manual smoke check minimum)

- No new TypeScript or lint errors introduced

- Documented in `README.md` or in `core-logic` JSDoc where relevant

# 2. Epic Summary

| Epic | Title | Phase focus | Story count | Points (P0) |
| --- | --- | --- | --- | --- |
| E1 | Foundations and Tooling | Prototype | 6 | 13 |
| E2 | Core-Logic Shared Package | Prototype | 7 | 15 |
| E3 | Database and Migrations | Prototype | 5 | 10 |
| E4 | Authentication and Sessions | Prototype | 6 | 13 |
| E5 | Multi-Tenant API Layer | Prototype | 5 | 11 |
| E6 | School and User Management | Prototype + MVP | 6 | 10 |
| E7 | Student Records | Prototype + MVP | 5 | 9 |
| E8 | Attendance | Prototype + MVP | 6 | 13 |
| E9 | M-Pesa Daraja Integration | Prototype | 6 | 16 |
| E10 | Access Tokens and Enforcement | Prototype | 5 | 11 |
| E11 | Sync (Push) | Prototype | 5 | 13 |
| E12 | Sync (Pull + Conflict) | MVP | 4 | 0 P0 |
| E13 | Desktop App (Electron + React) | Prototype | 8 | 18 |
| E14 | Mobile App (Expo Android) | Prototype | 8 | 18 |
| E15 | Demo Data and Seed | Prototype | 3 | 5 |
| E16 | Demo Polish and Scripts | Prototype | 4 | 6 |
| E17 | DevOps and Cloud Deployment | MVP | 5 | 0 P0 |
| E18 | Reporting and Roadmap | Post-MVP | Various | — |

Prototype effort estimate Roughly 180 points of P0 work across the prototype epics. At a sustained velocity of ~30 points per week for one senior engineer, that lands at 6 weeks — matching the timeline in the Blueprint.

# 3. Epic E1 — Foundations and Tooling

Lay down the monorepo, lint, type, and build pipelines so every later epic stops fighting the toolchain.

### US-E1-001 — Initialise the Turborepo monorepo

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 2 |
| Depends on | — |
| Linked SRS | Constraint |

As a developer,

I want to a working Turborepo + pnpm workspace skeleton with apps/ and packages/ slots,

so that downstream epics can scaffold their packages without re-discussing layout.

Acceptance criteria:

- `pnpm install` succeeds from a fresh clone

- `pnpm turbo run build` finds all packages and runs in topological order

- `pnpm-workspace.yaml` includes both `apps/*` and `packages/*`

- `turbo.json` pipeline declares `core-logic#build` before any app build

### US-E1-002 — Add base TypeScript config

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 1 |
| Depends on | US-E1-001 |
| Linked SRS | Constraint |

As a developer,

I want to a shared `tsconfig.base.json` with strict mode and path aliases,

so that every package inherits the same compiler rules without duplication.

Acceptance criteria:

- `strict: true` and `noUncheckedIndexedAccess: true` enabled

- Path alias `@sms/core-logic` resolves to `packages/core-logic/src/index.ts`

- Every app `tsconfig.json` extends the base

### US-E1-003 — Add lint and format config

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 2 |
| Depends on | US-E1-001 |
| Linked SRS | — |

As a developer,

I want to ESLint + Prettier wired into the monorepo with a single `pnpm lint` command,

so that code style stops being a debate.

Acceptance criteria:

- ESLint config extends `eslint:recommended`, `@typescript-eslint/recommended`, and React rules in client packages

- Prettier config consistent across packages

- `pnpm lint` exits clean on a fresh scaffold

- Pre-commit hook (husky or simple-git-hooks) runs `lint-staged`

### US-E1-004 — Add Jest base config

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 2 |
| Depends on | US-E1-002 |
| Linked SRS | — |

As a developer,

I want to Jest configured for `core-logic` and `apps/api` with one root command,

so that tests run before they are written, not after.

Acceptance criteria:

- `pnpm test` runs all packages

- Coverage report generated under `coverage/`

- Sample test passes in `core-logic`

### US-E1-005 — Add Docker Compose for local Postgres + pgAdmin

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 2 |
| Depends on | US-E1-001 |
| Linked SRS | — |

As a developer,

I want to a `docker-compose.yml` that spins up Postgres 16, pgAdmin, and reserves a slot for the API container,

so that every developer gets the same local DB without manual setup.

Acceptance criteria:

- `docker compose up postgres pgadmin` brings both up cleanly

- Postgres data volume is named and persistent

- pgAdmin pre-registers the local Postgres connection

- Healthcheck defined on Postgres service

### US-E1-006 — Configure root package scripts

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 1 |
| Depends on | US-E1-001, US-E1-003, US-E1-004 |
| Linked SRS | — |

As a developer,

I want to convenience scripts: `pnpm dev`, `pnpm build`, `pnpm test`, `pnpm lint`, `pnpm typecheck`,

so that a new contributor can be productive in five minutes.

Acceptance criteria:

- Each script runs via Turbo with `--filter` where appropriate

- Documented in root README

# 4. Epic E2 — Core-Logic Shared Package

Schemas, IDs, pricing, validity. The package is the single source of truth for business rules and ships to both the API and the clients.

### US-E2-001 — Set up @sms/core-logic package skeleton

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 1 |
| Depends on | US-E1-002 |
| Linked SRS | — |

As a developer,

I want to a `packages/core-logic` workspace package that builds to ESM and exports types,

so that downstream packages can import `@sms/core-logic` immediately.

Acceptance criteria:

- `packages/core-logic/package.json` named `@sms/core-logic`

- Builds to `dist/` via tsc

- `index.ts` re-exports submodules

### US-E2-002 — Implement UUID v7 newId() helper

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 1 |
| Depends on | US-E2-001 |
| Linked SRS | Constraint |

As a developer,

I want to a `newId(): string` function returning RFC 9562 UUID v7 values,

so that every entity gets time-sortable, sync-safe IDs without auto-increment.

Acceptance criteria:

- Uses `uuid` v10+ `v7()` under the hood

- Returns lowercase canonical string

- Unit test: 10,000 calls produce strictly increasing values when compared as strings (within same ms tolerance)

### US-E2-003 — Implement termFromDate() helper

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 1 |
| Depends on | US-E2-001 |
| Linked SRS | — |

As a developer,

I want to a function returning `term1 | term2 | term3` based on Kenyan school calendar dates,

so that term-based reporting (P1) needs a single trusted definition.

Acceptance criteria:

- Returns `term1` for Jan–Apr, `term2` for May–Aug, `term3` for Sep–Dec (placeholder; ranges editable)

- Unit tests cover boundary days

### US-E2-004 — Define Zod schemas (Tenant, User, Student, AccessToken)

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 3 |
| Depends on | US-E2-002 |
| Linked SRS | FR-TENANT-004, FR-SCHOOL-001, FR-STU-001, FR-PAY-004 |

As a developer,

I want to strict Zod schemas with inferred types exported alongside,

so that the API and the clients validate identically with the same definition.

Acceptance criteria:

- All schemas use `z.object().strict()`

- Every schema includes `schoolId: z.string().uuid()`

- Inferred types are re-exported via `types/index.ts`

- Unit tests: valid examples parse; invalid examples fail with predictable error paths

### US-E2-005 — Implement priceKES(role, pass) pricing function

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 2 |
| Depends on | US-E2-001 |
| Linked SRS | Pricing rules |

As a developer,

I want to a deterministic function returning the KES amount for (role, pass),

so that pricing changes only in one place across the codebase.

Acceptance criteria:

- teacher: day=10, week=50, month=150; admin: day=50, week=200, month=600

- Unknown combination throws with a clear error

- Unit tests cover the full matrix

### US-E2-006 — Implement accessDurationHours(pass) helper

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 1 |
| Depends on | US-E2-001 |
| Linked SRS | — |

As a developer,

I want to a function returning duration in hours for day/week/month,

so that the access-token service uses one source of truth for validity windows.

Acceptance criteria:

- day=24, week=168, month=720

- Unit-tested with all three values

### US-E2-007 — Implement isAccessValid(token) rule

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 2 |
| Depends on | US-E2-004, US-E2-006 |
| Linked SRS | FR-ACC-001 |

As a developer,

I want to a function that returns true iff token.validUntil > now,

so that every guard, every UI badge uses the same source of truth.

Acceptance criteria:

- Accepts an AccessToken object validated by AccessTokenSchema

- Edge case: validUntil = now returns false (strict greater-than)

- Edge case: missing fields throws via Zod, not silently false

- Unit-tested with frozen Date.now

### US-E2-008 — Reach ≥ 80% line coverage in core-logic

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 3 |
| Depends on | US-E2-002, US-E2-004, US-E2-005, US-E2-006, US-E2-007 |
| Linked SRS | — |

As a developer,

I want to comprehensive Jest tests across rules, schemas, and utils,

so that core-logic correctness is non-negotiable; it is reused everywhere.

Acceptance criteria:

- Coverage report shows ≥ 80% lines, ≥ 70% branches

- CI gate fails if coverage drops

# 5. Epic E3 — Database and Migrations

### US-E3-001 — Wire TypeORM in apps/api

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 2 |
| Depends on | US-E1-005 |
| Linked SRS | — |

As a developer,

I want to TypeORM module configured to read `DATABASE_URL` and synchronize=false (migrations only),

so that no surprise schema drift from auto-sync in any environment.

Acceptance criteria:

- `TypeOrmModule.forRootAsync` configured with env

- Logging level set via env

- `synchronize: false` in all environments

### US-E3-002 — Create initial migration: tenants, users, students

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 1 |
| Story points | 3 |
| Depends on | US-E3-001, US-E2-004 |
| Linked SRS | FR-SCHOOL-001, FR-STU-001 |

As a developer,

I want to the foundational tables with UUID PKs, indexes, and FKs,

so that all later features have somewhere to write.

Acceptance criteria:

- All three tables created with `id UUID PRIMARY KEY`

- `schoolId` FK on users and students

- Indexes: users(school_id), students(school_id)

- Migration runs and rolls back cleanly in test DB

### US-E3-003 — Create migration: access_tokens, payments

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 2 |
| Depends on | US-E3-002 |
| Linked SRS | FR-PAY-003, FR-PAY-004 |

As a developer,

I want to tables for payment lifecycle and access tokens,

so that M-Pesa flow has a place to land.

Acceptance criteria:

- access_tokens with index on (user_id, valid_until DESC)

- payments with UNIQUE index on mpesa_receipt

- FKs to users and tenants

### US-E3-004 — Create migration: attendance

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 2 |
| Depends on | US-E3-002 |
| Linked SRS | FR-ATT-001 |

As a developer,

I want to the attendance table with status enum and synced_at,

so that the prototype's most-demoed feature has storage.

Acceptance criteria:

- Status is a VARCHAR with CHECK or enum constraint

- Indexes: (school_id, date), (student_id, date)

- `synced_at` nullable

### US-E3-005 — Add RLS policies (P1)

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 3 |
| Depends on | US-E3-002, US-E3-003, US-E3-004 |
| Linked SRS | FR-TENANT-005 |

As a developer,

I want to PostgreSQL Row Level Security policies on tenant-scoped tables,

so that defence in depth: even a buggy query can't leak across tenants.

Acceptance criteria:

- Policies filter by `school_id = current_setting('app.school_id')::uuid`

- API sets the setting per request via interceptor

- Integration test: direct DB query without the setting returns 0 rows

# 6. Epic E4 — Authentication and Sessions

### US-E4-001 — Implement password hashing

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 1 |
| Depends on | — |
| Linked SRS | FR-AUTH-004, NFR-SEC-002 |

As a API developer,

I want to a bcrypt-backed `hash()` / `compare()` service,

so that passwords are never stored or logged in plaintext.

Acceptance criteria:

- bcrypt cost 12

- Unit test: hash differs each call; compare returns true for same input

### US-E4-002 — Implement POST /auth/login

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 3 |
| Depends on | US-E4-001, US-E3-002 |
| Linked SRS | FR-AUTH-001, FR-AUTH-002, FR-AUTH-003 |

As a user,

I want to to exchange phone + password for an access token and refresh token,

so that I can sign into the app.

Acceptance criteria:

- Valid credentials return `{ accessToken, refreshToken, user }` with 200

- Invalid credentials return 401 with `{ code: INVALID_CREDENTIALS }`

- Access token JWT has 15-minute expiry

- Refresh token persisted server-side with 7-day expiry

- Integration test covers both paths

### US-E4-003 — Implement JWT strategy and `@CurrentUser()`

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 2 |
| Depends on | US-E4-002 |
| Linked SRS | — |

As a API developer,

I want to a Passport JWT strategy plus a decorator that injects the authenticated user,

so that every protected controller stays one line.

Acceptance criteria:

- JWT strategy validates signature and expiry

- `@CurrentUser()` parameter decorator returns the user record

- Unauthenticated request to a protected route returns 401

### US-E4-004 — Implement POST /auth/refresh

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 2 |
| Depends on | US-E4-002 |
| Linked SRS | FR-AUTH-003 |

As a user,

I want to to silently refresh my access token without re-logging in,

so that I don't get bounced out every 15 minutes.

Acceptance criteria:

- Valid refresh token issues a new access token

- Refresh token rotates on use

- Expired or revoked refresh token returns 401

### US-E4-005 — Implement POST /auth/logout

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 1 |
| Depends on | US-E4-004 |
| Linked SRS | FR-AUTH-005 |

As a user,

I want to to end my session deterministically,

so that shared devices stay safe.

Acceptance criteria:

- Refresh token marked revoked

- Subsequent refresh returns 401

### US-E4-006 — SMS OTP password reset

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 5 |
| Depends on | — |
| Linked SRS | FR-AUTH-006 |

As a user,

I want to to reset my password via an OTP sent to my M-Pesa-registered phone,

so that I never have to call the school admin to unlock my account.

Acceptance criteria:

- OTP delivered to phone in < 60s

- OTP expires in 5 minutes

- Max 3 attempts per OTP, then a fresh request needed

# 7. Epic E5 — Multi-Tenant API Layer

### US-E5-001 — Implement TenantGuard

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 2 |
| Depends on | US-E3-002 |
| Linked SRS | FR-TENANT-001, FR-TENANT-002 |

As a API developer,

I want to a guard that reads `X-School-ID`, validates it, and attaches `schoolId` to the request,

so that every controller can trust the schoolId on the request.

Acceptance criteria:

- Missing header → 400 with `{ code: MISSING_SCHOOL_ID }`

- Malformed UUID → 400 with `{ code: INVALID_SCHOOL_ID }`

- Unknown schoolId → 404 with `{ code: SCHOOL_NOT_FOUND }`

- Valid → request.schoolId set, downstream code uses it

- Unit tests cover all four paths

### US-E5-002 — Implement `@SchoolId()` parameter decorator

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 1 |
| Depends on | US-E5-001 |
| Linked SRS | — |

As a API developer,

I want to a decorator that surfaces the request's schoolId in controllers,

so that controllers don't reach into the raw request.

Acceptance criteria:

- Decorator returns `request.schoolId` typed as string

- Throws if used without TenantGuard upstream

### US-E5-003 — Apply TenantGuard globally to feature modules

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 2 |
| Depends on | US-E5-001, US-E4-003 |
| Linked SRS | FR-TENANT-003 |

As a API developer,

I want to TenantGuard applied to every feature controller (except /auth, /payments/callback),

so that no controller can accidentally skip the check.

Acceptance criteria:

- Decorator or module-level binding makes the default protected

- Auth and Daraja callback routes opt out explicitly

- Integration test: GET /students without header returns 400

### US-E5-004 — Cross-tenant request rejection test

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 2 |
| Depends on | US-E5-003 |
| Linked SRS | FR-TENANT-003, UC-05 |

As a QA / developer,

I want to an automated test proving a Tenant A JWT cannot access Tenant B data,

so that this is the headline security guarantee.

Acceptance criteria:

- Test seeds two tenants and one user in Tenant A

- GET /students with Tenant B's X-School-ID returns 403 or empty result (depending on implementation)

- Test runs in CI

### US-E5-005 — Request-scoped TenantContext provider

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 2 |
| Depends on | US-E5-001, US-E4-003 |
| Linked SRS | — |

As a API developer,

I want to a `TenantContext` injected as REQUEST-scoped, exposing schoolId and user,

so that services don't pass schoolId through every signature.

Acceptance criteria:

- Provider scoped REQUEST

- Used by at least one service (students or attendance)

# 8. Epic E6 — School and User Management

### US-E6-001 — GET /tenants/me

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 1 |
| Depends on | US-E5-003 |
| Linked SRS | — |

As a admin,

I want to to fetch my school's profile,

so that the dashboard can render school name and status.

Acceptance criteria:

- Returns name, tier, flatFeeStatus, contact

- Inaccessible without auth

### US-E6-002 — GET /users

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 1 |
| Depends on | US-E5-003 |
| Linked SRS | FR-SCHOOL-002 |

As a admin,

I want to to list users in my school,

so that I can see who has access.

Acceptance criteria:

- Returns users filtered by schoolId

- Excludes password hash from response

### US-E6-003 — POST /users (admin creates teacher/finance)

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 3 |
| Depends on | US-E6-002 |
| Linked SRS | FR-SCHOOL-002 |

As a admin,

I want to to create a new user with a role,

so that I onboard new staff without engineering involvement.

Acceptance criteria:

- Body: name, phone, role, password

- Phone validated as Kenyan format

- Password hashed; user persisted with schoolId from request

- Duplicate phone within tenant returns 409

### US-E6-004 — PATCH /users/:id

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 2 |
| Depends on | US-E6-003 |
| Linked SRS | FR-SCHOOL-003 |

As a admin,

I want to to edit a user's role, name, or active status,

so that staff change roles; I shouldn't recreate them.

Acceptance criteria:

- Partial updates supported

- Only admin role may update

- Deactivated user cannot log in

### US-E6-005 — Admin resets another user's password

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 3 |
| Depends on | — |
| Linked SRS | FR-SCHOOL-005 |

As a admin,

I want to to set a temporary password for a user who has been locked out,

so that schools need a fallback when SMS OTP is unreachable.

Acceptance criteria:

- POST /users/:id/reset-password generates a temp password

- User flagged `mustChangePassword=true`; forced on next login

- Old refresh tokens revoked

### US-E6-006 — Self-service school sign-up

| Field | Value |
| --- | --- |
| Priority | P2 · Roadmap |
| Phase | Post-MVP |
| Story points | 8 |
| Depends on | — |
| Linked SRS | — |

As a new school,

I want to to sign up online without a sales call,

so that the funnel can grow without manual onboarding.

Acceptance criteria:

- Public landing page → email verification → first admin user

- Captcha or rate limit to prevent spam tenants

# 9. Epic E7 — Student Records

### US-E7-001 — GET /students with filtering

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 2 |
| Depends on | US-E5-003 |
| Linked SRS | FR-STU-004 |

As a admin / teacher,

I want to a paginated list filterable by grade and name,

so that I can quickly find any student.

Acceptance criteria:

- Pagination via `page` and `pageSize`

- Search matches case-insensitive substring of name

- Grade filter exact-match

### US-E7-002 — POST /students (add student)

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 2 |
| Depends on | US-E7-001 |
| Linked SRS | FR-STU-001 |

As a admin,

I want to to enrol a new student with name, grade, DOB, guardian phone,

so that the roster is mine to manage.

Acceptance criteria:

- UUID v7 id assigned server-side (or honoured if client-generated, with validation)

- Required: name, grade; optional: DOB, guardianPhone

- Returns 201 with student object

### US-E7-003 — PATCH /students/:id (edit)

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 2 |
| Depends on | US-E7-002 |
| Linked SRS | FR-STU-002 |

As a admin,

I want to to update a student's profile,

so that details change over time (guardian phone, grade).

Acceptance criteria:

- Partial body; validated by Zod

- Concurrent edits: last write wins for now

### US-E7-004 — Archive (soft delete) a student

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 1 |
| Depends on | US-E7-003 |
| Linked SRS | FR-STU-003 |

As a admin,

I want to to remove a student from active rosters without losing history,

so that history matters and accidents happen.

Acceptance criteria:

- Sets `is_archived = true`

- Default list endpoints exclude archived

- `?includeArchived=true` reveals them

### US-E7-005 — Bulk CSV import students

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 5 |
| Depends on | — |
| Linked SRS | FR-STU-005 |

As a admin,

I want to to upload a CSV and create many students at once,

so that onboarding 300 students one-by-one isn't realistic.

Acceptance criteria:

- Endpoint accepts multipart/form-data CSV

- Per-row validation; reports row-level errors

- Partial success allowed; idempotent on retry

# 10. Epic E8 — Attendance

### US-E8-001 — POST /attendance (bulk submit)

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4 |
| Story points | 3 |
| Depends on | US-E7-002 |
| Linked SRS | FR-ATT-001 |

As a teacher,

I want to to submit attendance for my entire class in one request,

so that one tap per pupil, one save.

Acceptance criteria:

- Body is an array of `{ studentId, date, status, note? }`

- Validates each entry against AttendanceSchema

- Idempotent on (studentId, date): repeated calls update, not duplicate

### US-E8-002 — GET /attendance with filters

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4 |
| Story points | 2 |
| Depends on | US-E8-001 |
| Linked SRS | — |

As a admin / teacher,

I want to to query attendance by date, class, or student,

so that the dashboard and history views need data.

Acceptance criteria:

- Filters: date, studentId, teacherId, status

- Pagination

- Aggregated counts available via `?summary=true`

### US-E8-003 — Daily attendance summary on dashboard

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4 |
| Story points | 2 |
| Depends on | US-E8-002 |
| Linked SRS | FR-ATT-004 |

As a admin,

I want to to see today's present/absent/late counts at a glance,

so that the dashboard answers "is school on?" in one screen.

Acceptance criteria:

- Counts broken down by class (grade)

- Updates without page refresh after a sync arrives

### US-E8-004 — Edit window enforcement (until midnight)

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4 |
| Story points | 2 |
| Depends on | US-E8-001 |
| Linked SRS | FR-ATT-003 |

As a teacher,

I want to to correct mistakes for today only,

so that yesterday's records shouldn't be silently editable.

Acceptance criteria:

- Same-day edits succeed

- Past-day edits return 403 with `{ code: ATT_EDIT_WINDOW_CLOSED }`

### US-E8-005 — Attendance history (last 30 days)

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 3 |
| Depends on | — |
| Linked SRS | FR-ATT-005 |

As a admin,

I want to to view a student's attendance over the last month,

so that patterns inform parent conversations.

Acceptance criteria:

- Calendar view with status colour coding

- Exportable as CSV

### US-E8-006 — Late-entry approval workflow

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 5 |
| Depends on | — |
| Linked SRS | FR-ATT-006 |

As a teacher / admin,

I want to to request and approve out-of-window attendance edits,

so that real life requires legitimate corrections.

Acceptance criteria:

- Teacher request creates a pending change

- Admin sees inbox; approve or reject

- Audit row records the resolution

# 11. Epic E9 — M-Pesa Daraja Integration

### US-E9-001 — Daraja OAuth: fetch and cache access token

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 3 |
| Depends on | — |
| Linked SRS | — |

As a API developer,

I want to a service that fetches Daraja access tokens and caches them until just before expiry,

so that every STK Push call needs a valid bearer token, with minimum overhead.

Acceptance criteria:

- Reads `DARAJA_CONSUMER_KEY`/`SECRET` from env

- Calls Daraja `/oauth/v1/generate?grant_type=client_credentials`

- Caches token in memory, refreshes 30s before expiry

- Unit test mocks the HTTP layer

### US-E9-002 — DarajaService.stkPush()

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 3 |
| Depends on | US-E9-001 |
| Linked SRS | — |

As a API developer,

I want to a wrapper that builds the STK Push payload and submits it,

so that the payments service stays high-level.

Acceptance criteria:

- Builds correct password using shortcode + passkey + timestamp

- TransactionType: CustomerPayBillOnline

- AccountReference and TransactionDesc surface our internal payment ID

- Returns Daraja CheckoutRequestID

### US-E9-003 — POST /payments/initiate

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 3 |
| Depends on | US-E9-002, US-E2-005 |
| Linked SRS | FR-PAY-001, FR-PAY-002 |

As a user,

I want to to start a payment for a chosen pass,

so that I can buy sync access in one tap.

Acceptance criteria:

- Body validated: `{ pass, phone? }` (phone defaults to user.phone)

- Creates `payments` row with status=pending and amount from priceKES()

- Returns `{ paymentId, status: pending, checkoutRequestId }`

- STK Push appears on user's phone within 5s (sandbox)

### US-E9-004 — POST /payments/callback (idempotent)

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 2 |
| Story points | 5 |
| Depends on | US-E9-003, US-E3-003 |
| Linked SRS | FR-PAY-003, FR-PAY-004, NFR-REL-002 |

As a Daraja,

I want to to deliver the payment result reliably,

so that Safaricom may retry; we cannot double-issue tokens.

Acceptance criteria:

- Validates payload via Zod

- Looks up payment by CheckoutRequestID

- On success: stores MpesaReceiptNumber, sets status=success, issues access token via AccessTokenService, emits WebSocket event

- On failure: status=failed, reason recorded

- Duplicate callback for same MpesaReceiptNumber updates nothing and returns 200

- Integration test covers duplicate, success, failure

### US-E9-005 — WebSocket `access:granted` event

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 2 |
| Depends on | US-E9-004 |
| Linked SRS | FR-PAY-005 |

As a client,

I want to to know the moment my access token is live,

so that users don't poll; UX feels instant.

Acceptance criteria:

- Socket.IO room per user (`user:<userId>`)

- Emit `access:granted` with `{ validUntil }` on token issuance

- Client unit test using mock socket transitions UI state

### US-E9-006 — GET /payments (own history)

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 2 |
| Depends on | — |
| Linked SRS | FR-PAY-007 |

As a user,

I want to to see my recent payments and their status,

so that I can troubleshoot a missing access window without calling support.

Acceptance criteria:

- Returns last 90 days

- Includes M-Pesa receipt and pass type

# 12. Epic E10 — Access Tokens and Enforcement

### US-E10-001 — AccessTokenService.createAccessToken()

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 2 |
| Depends on | US-E3-003, US-E2-006 |
| Linked SRS | — |

As a API developer,

I want to a service that issues access tokens from (userId, role, pass, paymentRef),

so that the M-Pesa callback flow has a one-call hand-off.

Acceptance criteria:

- Computes validUntil = now + accessDurationHours(pass)

- Persists row with payment_ref

- Returns the persisted entity

### US-E10-002 — AccessGuard implementation

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 3 |
| Depends on | US-E10-001, US-E4-003, US-E5-001 |
| Linked SRS | FR-ACC-002, FR-ACC-003 |

As a API developer,

I want to a NestJS guard that allows the request iff a valid access token exists or the school's admin flat fee is active,

so that sync endpoints are reliably gated.

Acceptance criteria:

- Looks up most recent token for userId

- Calls `isAccessValid` from core-logic

- Allows admin role iff tenants.flatFeeStatus = 'active'

- On reject: 402 with `{ code: ACCESS_EXPIRED, upgradeUrl: /pay }`

### US-E10-003 — Apply AccessGuard to /sync/* routes

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 1 |
| Depends on | US-E10-002 |
| Linked SRS | — |

As a API developer,

I want to sync endpoints inherit AccessGuard,

so that no sync route can skip the access check.

Acceptance criteria:

- Controller decorator wires the guard

- Integration test: POST /sync/push without access → 402

### US-E10-004 — Admin manual token issuance (comp days, manual flat-fee onboarding)

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 3 |
| Depends on | — |
| Linked SRS | FR-PAY-008 |

As a admin,

I want to to grant access manually with a reason,

so that edge cases (paid by other means, troubleshooting).

Acceptance criteria:

- POST /access-tokens/manual with `{ userId, pass, reason }`

- Only admins permitted

- Audited in access log with the reason

### US-E10-005 — Token revocation

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 2 |
| Depends on | — |
| Linked SRS | FR-ACC-005 |

As a admin,

I want to to revoke an active access token immediately,

so that suspended users must lose sync immediately.

Acceptance criteria:

- POST /access-tokens/:id/revoke sets validUntil = now

- Takes effect on next sync attempt

# 13. Epic E11 — Sync (Push)

### US-E11-001 — PowerSync server connector setup

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3–4 |
| Story points | 5 |
| Depends on | US-E3-004 |
| Linked SRS | — |

As a developer,

I want to PowerSync configured to read from Postgres with tenant-filtered sync rules,

so that the prototype demonstrates the engine that the MVP will rely on.

Acceptance criteria:

- `sync_rules.yaml` filters every replicated table by `school_id`

- Connector reads from Postgres replica or primary

- Smoke test: a row inserted via API appears on a connected client

### US-E11-002 — Client SQLite schema mirrors Postgres

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3–4 |
| Story points | 3 |
| Depends on | — |
| Linked SRS | — |

As a client developer,

I want to an Expo/Electron SQLite schema with the same tables and a `is_dirty` flag,

so that offline writes are queueable for sync.

Acceptance criteria:

- Tables: users, students, attendance, access_tokens (read-only on client)

- All tables include `is_dirty BOOLEAN DEFAULT 0` and `synced_at` where applicable

- Schema initialised on first launch via migration

### US-E11-003 — Push dirty attendance to server

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4 |
| Story points | 3 |
| Depends on | US-E11-002, US-E10-003 |
| Linked SRS | FR-SYNC-001, FR-SYNC-003 |

As a teacher,

I want to my offline attendance to appear on the cloud the moment I have access,

so that the admin sees today's roll within seconds.

Acceptance criteria:

- Sync button finds dirty rows, batches them, POSTs to /sync/push (or PowerSync equivalent)

- On 200: rows marked clean and `synced_at` stamped

- On 402: client transitions to payment prompt

- On 5xx: rows remain dirty

### US-E11-004 — Sync progress UI

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 2 |
| Depends on | — |
| Linked SRS | FR-SYNC-006 |

As a user,

I want to to see how many records remain in a sync run,

so that large syncs feel responsive.

Acceptance criteria:

- Progress bar or `n of m` indicator

- Cancellable

### US-E11-005 — Sync state indicator on every screen

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4 |
| Story points | 2 |
| Depends on | US-E11-003 |
| Linked SRS | — |

As a user,

I want to to know my sync status without thinking about it,

so that I trust the system when I can see it working.

Acceptance criteria:

- Top bar shows: offline / online / paid (Xh left) / unpaid

- Colour-coded; tooltip explains state

# 14. Epic E12 — Sync (Pull + Conflict, MVP)

### US-E12-001 — Pull sync delta from server

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 5 |
| Depends on | — |
| Linked SRS | FR-SYNC-004 |

As a client,

I want to to receive changes made on other devices since my last sync,

so that multi-device schools see consistent state.

Acceptance criteria:

- Server returns changes since `?since=` timestamp

- Client applies them in order

- No data loss on interrupted pull

### US-E12-002 — Last-write-wins conflict resolution per entity

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 5 |
| Depends on | — |
| Linked SRS | FR-SYNC-004 |

As a client,

I want to deterministic resolution of conflicting edits,

so that two teachers editing the same record don't silently corrupt data.

Acceptance criteria:

- Per-entity policy; updated_at decides

- Loser's edit logged for audit

### US-E12-003 — Exponential backoff on failed sync

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 2 |
| Depends on | — |
| Linked SRS | FR-SYNC-005 |

As a client,

I want to retries that don't hammer the server during outages,

so that outages stay short and respectful of resources.

Acceptance criteria:

- Backoff schedule e.g. 5s, 15s, 60s, 5min

- User can force retry

### US-E12-004 — Selective sync (term-scoped on mobile)

| Field | Value |
| --- | --- |
| Priority | P2 · Roadmap |
| Phase | Post-MVP |
| Story points | 5 |
| Depends on | — |
| Linked SRS | FR-SYNC-007 |

As a teacher,

I want to only this term's data on my phone,

so that storage and bandwidth are precious.

Acceptance criteria:

- Configurable per role

- Old data still accessible on demand from cloud

# 15. Epic E13 — Desktop App (Electron + React)

### US-E13-001 — Electron + Vite + React skeleton

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 3 |
| Depends on | US-E1-001 |
| Linked SRS | — |

As a developer,

I want to a working Electron shell loading a Vite+React renderer,

so that all desktop UI lives somewhere.

Acceptance criteria:

- `pnpm --filter desktop dev` opens an Electron window

- Hot reload works

- Production build produces an installer for Windows

### US-E13-002 — Login screen

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 2 |
| Depends on | US-E13-001, US-E4-002 |
| Linked SRS | — |

As a admin,

I want to a login form with phone and password,

so that I can authenticate from the desktop.

Acceptance criteria:

- Form validates on the client (Zod) before submit

- Success navigates to dashboard

- Failure shows actionable error

### US-E13-003 — Dashboard with attendance summary

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 3 |
| Depends on | US-E13-002, US-E8-003 |
| Linked SRS | — |

As a admin,

I want to today's roll counts and recent syncs at a glance,

so that the daily routine starts here.

Acceptance criteria:

- Counts by class (grade) for today

- Recent 5 sync events visible

- Empty states clear ("No attendance yet today")

### US-E13-004 — Students screen (list, add, edit, archive)

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 3 |
| Depends on | US-E13-002, US-E7-002, US-E7-003, US-E7-004 |
| Linked SRS | — |

As a admin,

I want to to manage the student roster,

so that this is the system of record.

Acceptance criteria:

- Search and grade filter

- Add and edit modals validated against StudentSchema

- Archive with undo (5s)

### US-E13-005 — Users screen (list, add, edit)

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 3 |
| Story points | 2 |
| Depends on | US-E13-002, US-E6-003 |
| Linked SRS | — |

As a admin,

I want to to onboard staff,

so that I need control over who has access.

Acceptance criteria:

- List filterable by role

- Add modal with role picker

### US-E13-006 — Access Log screen

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4 |
| Story points | 2 |
| Depends on | US-E13-002, US-E9-004 |
| Linked SRS | — |

As a admin,

I want to a chronological view of all payments and access windows,

so that every shilling and every access is traceable.

Acceptance criteria:

- Columns: when, who, pass, amount, M-Pesa receipt, valid window

- Filter by user and date range

- Empty state explains how rows appear

### US-E13-007 — Local SQLite + offline reads on desktop

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4 |
| Story points | 3 |
| Depends on | US-E13-001, US-E11-002 |
| Linked SRS | — |

As a admin,

I want to the desktop to work without internet for reads,

so that schools shouldn't lose their dashboard when wifi blips.

Acceptance criteria:

- Read-side queries hit SQLite first

- Network calls only for sync and payments

### US-E13-008 — Standalone Electron mode toggle (P1)

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 8 |
| Depends on | — |
| Linked SRS | FR-OFFLINE-005 |

As a admin,

I want to to run the desktop with no cloud connection at all,

so that very-remote schools may opt out of cloud entirely.

Acceptance criteria:

- Toggle in Settings; persisted

- When on, hides sync UI; disables payment endpoints

- Documented limitations clear to user

# 16. Epic E14 — Mobile App (Expo, Android)

### US-E14-001 — Expo skeleton with Android build

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4 |
| Story points | 3 |
| Depends on | US-E1-001 |
| Linked SRS | — |

As a developer,

I want to an Expo app that builds and runs on a real Android device,

so that every teacher feature ships from here.

Acceptance criteria:

- `pnpm --filter mobile start` launches Expo

- APK builds via `eas build --platform android --profile preview`

- Runs on baseline 2 GB device without crashing

### US-E14-002 — Login screen (phone + password)

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4 |
| Story points | 2 |
| Depends on | US-E14-001, US-E4-002 |
| Linked SRS | — |

As a teacher,

I want to to sign in with the phone number my admin set up,

so that first impression of the app.

Acceptance criteria:

- Phone accepts +254… or 07…; normalises on submit

- Forgot password CTA points to admin reset path (P1: SMS OTP)

### US-E14-003 — Class roster + attendance capture

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4–5 |
| Story points | 5 |
| Depends on | US-E14-002, US-E8-001, US-E11-002 |
| Linked SRS | — |

As a teacher,

I want to to mark each student present, absent, or late with one tap,

so that speed is the whole point.

Acceptance criteria:

- Roster loaded from local SQLite

- Tap cycles Present → Absent → Late

- Save button persists immediately, even offline

- Visual confirmation on save

### US-E14-004 — Sync button + state indicator

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4–5 |
| Story points | 2 |
| Depends on | US-E14-003, US-E11-003, US-E11-005 |
| Linked SRS | — |

As a teacher,

I want to a sync button that shows my access state and triggers sync,

so that I always know whether I'm paid up.

Acceptance criteria:

- Button shows: "Sync (paid, 4h left)" or "Sync (pay required)"

- On 402, opens the payment modal directly

### US-E14-005 — M-Pesa payment modal (pass selection + initiate)

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 4–5 |
| Story points | 3 |
| Depends on | US-E14-004, US-E9-003 |
| Linked SRS | — |

As a teacher,

I want to to buy a day/week/month pass without leaving the app,

so that payment friction is the conversion killer.

Acceptance criteria:

- Three pass options with KES prices from priceKES()

- Confirms phone number, calls /payments/initiate

- Shows "Waiting for confirmation…" with cancel

### US-E14-006 — Listen for `access:granted` WebSocket

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 5 |
| Story points | 2 |
| Depends on | US-E14-005, US-E9-005 |
| Linked SRS | — |

As a teacher,

I want to the app to unlock automatically the moment my payment lands,

so that magical UX = high conversion.

Acceptance criteria:

- Socket connects on login; reconnects on network resume

- Receiving access:granted closes payment modal, triggers sync

### US-E14-007 — Offline indicator + retry queue

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 5 |
| Story points | 2 |
| Depends on | US-E14-003 |
| Linked SRS | FR-OFFLINE-003 |

As a teacher,

I want to to know I'm offline and that my work is safe,

so that trust.

Acceptance criteria:

- Detects connectivity loss within 2s

- Shows a non-intrusive banner

- Queued ops list available in Settings

### US-E14-008 — App icon, splash, theme polish

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 5 |
| Story points | 1 |
| Depends on | US-E14-001 |
| Linked SRS | — |

As a demo lead,

I want to the app to look credible in a demo,

so that first impressions sway stakeholders.

Acceptance criteria:

- Branded splash screen

- Consistent colour palette

- Adaptive icon for Android

# 17. Epic E15 — Demo Data and Seed

### US-E15-001 — Seed script: 1 school + users

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 5 |
| Story points | 2 |
| Depends on | US-E3-002, US-E6-003 |
| Linked SRS | — |

As a demo lead,

I want to a one-command seed that creates Riverbank Academy with one admin, two teachers, one finance,

so that every demo starts identical.

Acceptance criteria:

- `pnpm seed` resets DB and seeds users

- Passwords printed to stdout for demo use

### US-E15-002 — Seed: 30 students across Grades 3–6

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 5 |
| Story points | 1 |
| Depends on | US-E15-001 |
| Linked SRS | — |

As a demo lead,

I want to realistic Kenyan names spread over four grades,

so that the demo looks like a real school.

Acceptance criteria:

- Names from a small curated list (Kenyan-first-name + Kenyan-surname)

- Even spread across grades

### US-E15-003 — Seed: 2 weeks of attendance + 3 access tokens

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 5 |
| Story points | 2 |
| Depends on | US-E15-002 |
| Linked SRS | — |

As a demo lead,

I want to history that makes the dashboard interesting and the access log realistic,

so that the dashboard isn't empty on first launch.

Acceptance criteria:

- ~150 attendance rows (some absences and late marks)

- One expired token, one active (admin flat-fee), one fresh from M-Pesa sandbox

# 18. Epic E16 — Demo Polish and Scripts

### US-E16-001 — Write DEMO_SCRIPT.md

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 5 |
| Story points | 1 |
| Depends on | — |
| Linked SRS | — |

As a demo lead,

I want to a step-by-step walkthrough of all five demo scenarios,

so that anyone on the team can deliver the demo.

Acceptance criteria:

- One page per scenario

- Includes screenshots from the prototype

- Lists the exact talking point for each step

### US-E16-002 — Internal dry-run with team

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 5 |
| Story points | 1 |
| Depends on | — |
| Linked SRS | — |

As a team,

I want to to run the full demo internally and capture issues,

so that no live demo runs untested.

Acceptance criteria:

- Issues triaged within 24h

- Critical issues fixed before stakeholder demo

### US-E16-003 — Record Loom (leave-behind)

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 6 |
| Story points | 2 |
| Depends on | US-E16-001 |
| Linked SRS | — |

As a demo lead,

I want to a 10-minute screen recording covering the prototype,

so that stakeholders can re-watch and share.

Acceptance criteria:

- Audio-narrated by the demo lead

- Captioned for accessibility

- Hosted privately; link in handover

### US-E16-004 — Fallback "simulate payment" admin toggle

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 6 |
| Story points | 2 |
| Depends on | — |
| Linked SRS | — |

As a demo lead,

I want to to skip the live M-Pesa step if Daraja sandbox is misbehaving,

so that no demo dies because of someone else's infra.

Acceptance criteria:

- Hidden admin-only endpoint issues an access token directly

- UI button only visible with a specific env flag

- Used only as last resort during demo

# 19. Epic E17 — DevOps and Cloud Deployment (MVP)

### US-E17-001 — Dockerise the API

| Field | Value |
| --- | --- |
| Priority | P0 · Prototype |
| Phase | Week 5 |
| Story points | 2 |
| Depends on | — |
| Linked SRS | — |

As a developer,

I want to a multi-stage Dockerfile producing a small, secure image,

so that the same image runs locally and in Cloud Run.

Acceptance criteria:

- Image ≤ 200 MB

- Non-root user

- Healthcheck endpoint reachable

### US-E17-002 — GitHub Actions CI: lint, test, build

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 3 |
| Depends on | — |
| Linked SRS | — |

As a developer,

I want to every PR to fail loudly on regressions,

so that the team trusts main.

Acceptance criteria:

- Workflow runs lint, test, build on push and PR

- Caches pnpm store

- Status checks required before merge

### US-E17-003 — Cloud Run deploy via GitHub Actions (WIF)

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 5 |
| Depends on | — |
| Linked SRS | — |

As a developer,

I want to automated deploys to GCP using Workload Identity Federation,

so that no long-lived service account keys.

Acceptance criteria:

- Push to main → image to Artifact Registry → revision on Cloud Run

- Migrations run as a Cloud Run Job before serving traffic

- Rollback documented

### US-E17-004 — Cloud SQL provisioning

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 3 |
| Depends on | — |
| Linked SRS | — |

As a DevOps,

I want to a managed Postgres 16 instance in africa-south1,

so that production data lives somewhere reliable.

Acceptance criteria:

- Private IP, automated backups daily, PITR

- Connection from Cloud Run via Cloud SQL Auth Proxy or private VPC

### US-E17-005 — Monitoring + error reporting

| Field | Value |
| --- | --- |
| Priority | P1 · MVP |
| Phase | Post-prototype |
| Story points | 2 |
| Depends on | — |
| Linked SRS | — |

As a DevOps,

I want to Cloud Logging plus Error Reporting hooked up,

so that we know when things break in production.

Acceptance criteria:

- Structured logs (JSON) from API

- Errors create incidents in Error Reporting

- Email or Slack alert on new-error class

# 20. Epic E18 — Reporting and Roadmap (Post-MVP)

These items are tracked but not estimated in detail. They become well-formed user stories once MVP feedback shapes them.

- Term and year academic reporting

- Parent portal (read-only attendance + announcements)

- Grades and report cards

- Fee management module (with separate M-Pesa flow)

- iOS build of the mobile app

- Swahili localisation

- Bulk import from school spreadsheets / NEMIS export

- Self-service school sign-up funnel

- Multi-school groupings (federations, dioceses)

- Penetration test and OWASP review

- Disaster recovery and multi-region

# 21. Traceability Matrix

Cross-reference between SRS functional requirements and backlog stories. Use to audit coverage before sprint planning.

| SRS FR | Stories | Phase |
| --- | --- | --- |
| FR-AUTH-001..005 | US-E4-001 … US-E4-005 | Prototype |
| FR-AUTH-006 | US-E4-006 | MVP |
| FR-TENANT-001..004 | US-E5-001 … US-E5-005 | Prototype |
| FR-TENANT-005..006 | US-E3-005, US-E11-001 | MVP |
| FR-SCHOOL-001..003 | US-E6-001 … US-E6-003 | Prototype |
| FR-SCHOOL-004..005 | US-E6-004, US-E6-005 | MVP |
| FR-SCHOOL-006 | US-E6-006 | Roadmap |
| FR-STU-001..004 | US-E7-001 … US-E7-004 | Prototype |
| FR-STU-005..006 | US-E7-005, (photo TBD) | MVP |
| FR-ATT-001..004 | US-E8-001 … US-E8-004 | Prototype |
| FR-ATT-005..006 | US-E8-005, US-E8-006 | MVP |
| FR-OFFLINE-001..004 | US-E13-007, US-E14-007, US-E11-002 | Prototype + MVP |
| FR-OFFLINE-005 | US-E13-008 | MVP |
| FR-SYNC-001..003 | US-E11-003 … US-E11-005 | Prototype |
| FR-SYNC-004..006 | US-E12-001, US-E12-002, US-E11-004, US-E12-003 | MVP |
| FR-PAY-001..006 | US-E9-001 … US-E9-005 | Prototype |
| FR-PAY-007..008 | US-E9-006, US-E10-004 | MVP |
| FR-ACC-001 | US-E2-007 | Prototype |
| FR-ACC-002..003 | US-E10-001 … US-E10-003 | Prototype |
| FR-ACC-004..005 | US-E10-005 | MVP |
| FR-AUDIT-001 | US-E13-006 | Prototype |
| FR-AUDIT-002..003 | US-E17-005, audit tables (MVP) | MVP |